## Backlog
ID | Page | Feature Description | Priority | Status (Pending/In Progress/Closed) | Completion Date | Tested Date | Comment
1 | - | Navigation | - | Closed | 2023-01-21 |  | -
2 | - | Setup GitHub Repo | - | Closed | 2023-01-22 |  | -
3 | Home | Display number of rows & columns | - | Closed | 2023-01-22 |  | -
4 | Home | Display raw input dataset | - | Closed | 2023-01-22 |  | -
5 | Confirm Input Dataset | Show a dropdown of all columns | - | Closed | 2023-01-22 |  | -
6 | Confirm Input Dataset | Show dataset with selected predictor variable columns | - | Closed | 2023-01-23 |  | -
7 | Confirm Input Dataset | Show confirm predictor variables type list | - | Closed | 2023-01-23 |  | -
8 | Confirm Input Dataset | Show save button | - | Closed | 2023-01-22 |  | -
9 | Confirm Input Dataset | Hide dataset column(s) on change of dropdown | - | Closed | 2023-02-21 |  | -
10 | Confirm Input Dataset | Hide confirm predictor variables type on change of dropdown | - | Closed | 2023-02-21 |  | -
11 | Confirm Input Dataset | Save input dataset info in shared storage | - | Closed | 2023-02-21 |  | -
12 | Confirm Input Dataset | Validate if any column with dtype 'object' marked as numerical before save | - | Closed | 2023-03-19
13 | Confirm Input Dataset | Show error message when user input is invalid | - | Closed | 2023-03-19
14 | Good/Bad Definition | Show define bad & indeterminate & good definition UI | - | Closed | 2023-03-18 |  | -
15 | Good/Bad Definition | Show confirm definitions button | - | Closed | 2023-03-16 |  | -
16 | Good/Bad Definition | Add definition row when add button is clicked for bad & indeterminate definition | - | Closed | 2023-03-18 |  | -
17 | Good/Bad Definition | Remove definition row when remove button is clicked for bad & indeterminate definitions |  | Pending |  |  | Require installation of dash-renderer in code environment, not sure why but even in local computer, intallation gets error
18 | Good/Bad Definition | Save numerical definition when confirm button is clicked | - | Closed | 2023-03-18 |  | -
19 | Good/Bad Definition | Save categorical definition when confirm button is clicked | - | Closed | 2023-03-18 |  | -
20 | Good/Bad Definition | Show only numerical variable in dataset as dropdown options for bad numerical variables | - | Closed | 2023-03-16 |  | -
21 | Good/Bad Definition | Show only categorical variable in dataset as dropdown options for bad categorical variables | - | Closed | 2023-03-16 |  | -
22 | Good/Bad Definition | Update categorical options based on dropdown value | - | Pending |  |  | Require installation of dash-renderer in code environment, not sure why but even in local computer, intallation gets error
23 | Good/Bad Definition | Plan data structure for good bad definition | - | Closed | 2023-03-18 |  | -
24 | Good/Bad Definition | Merge numerical ranges before save | - | Closed | 2023-03-18 |  | -
25 | Good/Bad Definition | Merge categorical elements before save | - | Closed | 2023-03-18 |  | -
26 | Good/Bad Definition | Ensure upper bound > lower bound for numerical variables before save, does not save if violated | - | Closed | 2023-03-19 |  | -
27 | Good/Bad Definition | If upper bound > lower bound is violated, show error message | - | Closed | 2023-03-19
28 | Good/Bad Definition | Validate any overlapping numerical user input between bad & indeterminate before data is saved | - | Closed | 2023-03-19
29 | Good/Bad Definition | Validate any overlapping categorical user input between bad & indeterminate before data is saved | - | Closed | 2023-03-19
30 | Good/Bad Definition | Show error message when overlapping numerical user input | - | Closed | 2023-03-19
31 | Good/Bad Definition | Show error message when overlapping categorical user input | - | Closed | 2023-03-19
32 | Good/Bad Definition | Bin dataset & save to shared storage
33 | Good/Bad Definition | Show statistics with class GoodBadCounter
34 | Good/Bad Definition | Show bar chart
35
36
37
38

## Bugs
ID | Page | Bug Description | Priority | Status (Pending/In Progress/Closed) | Fixed Date | Tested Date | Comment
1 | Interactive Binning | When user clicked on a bar with index greater than that of the number of bins the other predictor variable has, it cannot switch the chart when user select that other predictor variable | moderate | Pending

## Old Backlog
ID | Page | Feature Description | Priority | Status (Pending/In Progress/Closed) | Completion Date | Tested Date | Comment
1 | - | Navigation | - | Closed | 2023-01-21 |  | -
2 | - | Setup GitHub Repo | - | Closed | 2023-01-22 |  | -
3 | Home | Display number of rows & columns | - | Closed | 2023-01-22 |  | -
4 | Home | Display raw input dataset | - | Closed | 2023-01-22 |  | -
5 | Confirm Input Dataset | Show response variables found | - | Closed | 2023-01-22 |  | -
6 | Confirm Input Dataset | Show dropdown of predictor variables | - | Closed | 2023-01-22 |  | -
7 | Confirm Input Dataset | Show dataset with selected predictor variable columns | - | Closed | 2023-01-23 |  | -
8 | Confirm Input Dataset | Show confirm predictor variables type list | - | Closed | 2023-01-23 |  | -
9 | Confirm Input Dataset | Show save button | - | Closed | 2023-01-22 |  | -
10 | Confirm Input Dataset | Hide dataset column(s) on change of dropdown | - | Closed | 2023-02-21 |  | -
11 | Confirm Input Dataset | Hide confirm predictor variables type on change of dropdown | - | Closed | 2023-02-21 |  | -
12 | Confirm Input Dataset | Save input dataset info in shared storage | - | Closed | 2023-02-21 |  | -
13 | Good/Bad Definition | Show definition column dropdown | - | Closed | 2023-01-23 |  | -
14 | Good/Bad Definition | Show input area for weight of good & bad | - | Closed | 2023-01-23 |  | -
15 | Good/Bad Definition | Show slider for indeterminate range | - | Closed | 2023-01-23 |  | -
16 | Good/Bad Definition | Show save button | - | Closed | 2023-01-23 |  | -
17 | Good/Bad Definition | Show bar chart | - | Closed | 2023-01-23 |  | -
18 | Good/Bad Definition | Hide indeterminate range slider when 'loan_status' is selected | - | Closed | 2023-02-21 |  | -
19 | Good/Bad Definition | Auto-calculate weight of good when 'paid_past_due' is selected | - | Closed | 2023-01-23 |  | -
20 | Good/Bad Definition | Save good/bad definition in shared storage | - | Closed | 2023-01-23 |  | -
21 | Good/Bad Definition | Update the bar chart after confirm button is clicked | - | Closed | 2023-02-21 |  | -
22 | Interactive Binning | Show select predictor variable to be bin dropdown | - | Closed | 2023-01-24 |  | -
23 | Interactive Binning | Display only predictor variable confirmed in 'Confirm Inpute Dataset' page in the dropdown | - | Closed | 2023-02-21 |  | -
24 | Interactive Binning | Show a dropdown for selecting an automated binning algorithm | - | Closed | 2023-02-21 |  | -
25 | Interactive Binning | Update the description of the automated binning algorithm selected based on dropdown value | - | Closed | 2023-02-21 |  | -
26 | Interactive Binning | Show mixed chart | - | Closed | 2023-02-24 |  | requires further checking of computation for bin frequencies, and current WOE line is using dummy data
27 | Interactive Binning | Show control panel | - |  |  |  | -
28 | Preview & Download Settings | Show preview dataset | - | Closed | 2023-02-23 |  | -
29 | Preview & Download Settings | Download json bin settings button | - | Closed | 2023-02-23 |  | -
30 | Confirm Input Dataset | Initial binning & save result to shared storage - treat every value as a unique bin | - | Closed | 2023-02-23 |  | -
31 | Interactive Binning | Update computation of woe in mixed chart | -
32 | Interactive Binning | Show automated binning section UI | - | Closed | 2023-02-25
33 | Interactive Binning | Implement equal-width automated binning algorithm (based on width) | -
34 | Interactive Binning | Implement equal-width automated binning algorithm (based on number of bins) | -
35 | Interactive Binning | Implement equal-frequency automated binning algorithm (based on frequency) | -
36 | Interactive Binning | Implement equal-frequency automated binning algorithm (based on number of bins) | -
37 | Interactive Binning | Implement import-settings automated binning algorithm | -
38 | Interactive Binning | Show control panel UI | -
39 | Interactive Binning | Implement calculation for summary statistic table dataframe | -
40 | Interactive Binning | Show dummy summary statistical table (before & after) | -
41 | Interactive Binning | Update before & after summary statistical table | -
42 | Interactive Binning | Implement save interactive binning button | -
43 | Interactive Binning | Implement split bin | -
44 | Interactive Binning | Implement merge bins | -
45 | Interactive Binning | Implement remove bins | -
46 | Interactive Binning | Implement rename bin | -
47 | Preview & Download Settings | Show finalized summary statistical table | -
48 | Preview & Download Settings | Show finalized mixed chart | -
49 | Good/Bad Definition | Show UI | - | Closed | 2023-03-08
50 | Good/Bad Definition | Dynamic add and remove definition row | - | In Progress