## Sheet1
ID | Page | Feature Description | Current Priority | Status (Pending/In Progress/Closed) | Completion Date | Tested Date | Comment
1 | - | Navigation | - | Closed | 2023-01-21 |  | -
2 | - | Setup GitHub Repo | - | Closed | 2023-01-22 |  | -
3 | Home | Display number of rows & columns | - | Closed | 2023-01-22 |  | -
4 | Home | Display raw input dataset | - | Closed | 2023-01-22 |  | -
5 | Confirm Input Dataset | Show response variables found | - | Closed | 2023-01-22 |  | -
6 | Confirm Input Dataset | Show dropdown of predictor variables | - | Closed | 2023-01-22 |  | -
7 | Confirm Input Dataset | Show dataset with selected predictor variable columns | - | Closed | 2023-01-23 |  | -
8 | Confirm Input Dataset | Show confirm predictor variables type list | - | Closed | 2023-01-23 |  | -
9 | Confirm Input Dataset | Show save button | - | Closed | 2023-01-22 |  | -
10 | Confirm Input Dataset | Hide dataset column(s) on change of dropdown | - | Closed | 2023-02-21 |  | -
11 | Confirm Input Dataset | Hide confirm predictor variables type on change of dropdown | - | Closed | 2023-02-21 |  | -
12 | Confirm Input Dataset | Save input dataset info in shared storage | - | Closed | 2023-02-21 |  | -
13 | Good/Bad Definition | Show definition column dropdown | - | Closed | 2023-01-23 |  | -
14 | Good/Bad Definition | Show input area for weight of good & bad | - | Closed | 2023-01-23 |  | -
15 | Good/Bad Definition | Show slider for indeterminate range | - | Closed | 2023-01-23 |  | -
16 | Good/Bad Definition | Show save button | - | Closed | 2023-01-23 |  | -
17 | Good/Bad Definition | Show bar chart | - | Closed | 2023-01-23 |  | -
18 | Good/Bad Definition | Hide indeterminate range slider when 'loan_status' is selected | - | Closed | 2023-02-21 |  | -
19 | Good/Bad Definition | Auto-calculate weight of good when 'paid_past_due' is selected | - | Closed | 2023-01-23 |  | -
20 | Good/Bad Definition | Save good/bad definition in shared storage | - | Closed | 2023-01-23 |  | -
21 | Good/Bad Definition | Update the bar chart after confirm button is clicked | - | Closed | 2023-02-21 |  | -
22 | Interactive Binning | Show select predictor variable to be bin dropdown | - | Closed | 2023-01-24 |  | -
23 | Interactive Binning | Display only predictor variable confirmed in 'Confirm Inpute Dataset' page in the dropdown | - | Closed | 2023-02-21 |  | -
24 | Interactive Binning | Show a dropdown for selecting an automated binning algorithm | - | Closed | 2023-02-21 |  | -
25 | Interactive Binning | Update the description of the automated binning algorithm selected based on dropdown value | - | Closed | 2023-02-21 |  | -
26 | Interactive Binning | Show mixed chart | - | In Progress
27 | Interactive Binning | Show control panel | - | In Progress
28 | Preview & Download Settings | Show preview dataset | - | Closed | 2023-02-23
29 | Preview & Download Settings | Download json bin settings button | - | Closed | 2023-02-23
30 | (Backend) | Initial binning & save result to shared storage - treat every value as a unique bin | - | Closed | 2023-02-23